## Data (hidden)
Tester's Status | Developer's Status
Pass | Bug Fixed
Fail | Under Bug-Fixing Process
Under Testing | Functionality Clarified
Deferred | Deferred
On-Hold

## Instructions
I N S T R U C T I O N S
Please read below ALL instructions carefully before starting your RBI Tool testing…
1 | In all test cases, you only need to fill in the Green columns
2 | You must execute all the test cases in given sequence. If there is any comment /observation, please mention in the designated column
3 | If a test case is producing the desired output /result, you will select the tester status as "Pass"
4 | If a test case is not producing the desired results, you will select the tester status as "Fail"
5 | If testing is on-going and still not yet completed, you will select the tester status as "Under Testing"
6 | If a specific functionality is not required, you will select the tester status as "Deferred"
7 | If for any reason, a specific feature required is not yet confirmed from the team, you will select the tester status as "On-Hold"
8 | Inspector test cases are dependent on Admin test cases. Means First test the Admin Module and then Inspector Module
9 | Once Inspection is scheduled, now, Inspector can start his /her test cases accordingly.
10 | If you think some functionality is missing in the tool and as well as in test cases, please include same on the last sheet of Missing Functionality
11 | If you need to provide your observation on any of the test case, please provide your observation just next to the specific tester status column "Suggestions"
12 | In the Actual Results column, input the results of specific test case. If result are not as expected, please provide the data you used in that specific test case

## GDP Test Results Summary
GDP Admin Module - Tester Status |  | GDP Admin Module - Developer Status
Test Cases | Total | Test Cases | Total
Total Test Cases | 29 | Bug Fixed | 1
Total Passed | 19 | Under Bug-Fixing Process | 0
Total Failed | 1 | Functionality Clarified | 6
Total Under Testing | 4 | Deferred | 0
Total Deferred | 0
Total On-Hold | 0
GDP Inspector Module - Tester Status |  | GDP Inspector Module - Developer Status |  | PQM+ Team GDP Module Testing Credentials
Test Cases | Total | Test Cases | Total | Bangladesh NMRA
Total Test Cases | 27 | Bug Fixed | 4 | User Id | GKK@usp.org
Total Passed | 14 | Under Bug-Fixing Process | 0 | Password | 12345
Total Failed | 1 | Functionality Clarified | 3
Total Under Testing | 4 | Deferred | 0 | PQM+ Team GDP Module Testing Credentials
Benin NMRA
Total Deferred | 0 |  |  | User Id | TYN@usp.org
Total On-Hold | 0 |  |  | Password | 12345
GDP Mobile App - Tester Status |  | GDP Mobile App - Developer Status
Test Cases | Total | Test Cases | Total
Total Test Cases | 16 | Bug Fixed | 0
Total Passed | 0 | Under Bug-Fixing Process | 0
Total Failed | 0 | Functionality Clarified | 0
Total Under Testing | 0 | Deferred | 0
Total Deferred | 0
Total On-Hold | 0

## GDP Admin
Tester Name | Test Date | Test Case No. | Function Name | Subm Function | Pre-requisite | Test Description | Test Step Details /Data input | Expected Results | Actual Results | Tester Status | Suggestions | Developer's Response | Developer's Status
|  | 1 | Access RBI Tool URL | RBI Tool Test URL | 1. Internet Connection 2. Access the Google Chrome browser | To open the RBI Tool Landing page | Input this URL and press Enter key https://www.rbi-test.pqmplustools.com | Landing page of the RBI Tool |  | Pass
|  | 2 | I forgot my password | Forgot Password | 1. Test Case one is passed 2. Active Country Admin account | To reset your forgotten password | Below the Sign In button, click on I forgot my password link | System should take you to the RBI Tool password retrievel page |  | Pass
|  | 3 | I forgot my password | Forgot Password | 1. On the RBI password retrievel page 2. You email should be active email 3. Email should not be blocked | To reset your forgotten password | Input your Admin Email and Verification Code and Press the Request New Password button | You should receive an email for the confirmation of password reset. When you will confirm the email then you will get another email with new auto-generated password from the RBI Tool that you can use to login. |  | Under Testing | No email was received | This was very straight-forward to reset password. Is there something happening to complete this test case? Tim: No email was received on 5/20 test
|  | 4 | NMRA Admin Registration | Registration Process | 1. User is on the landing page 2. Email is an active email 3. Email is not blocked | Registration of an NMRA Admin Account | User will click on Register a new account link. User will see the Instructions for new registration. After reading the Instructions, user will click on the Proceed button to open the registration form. User will input all mandatory fields (indicated with red astrick) and will input the validation code. User will check the I agree to the terms and will click the Register button. | User should get an email from the RBI Tool indicating the receipt of the registration form and next process. PQM+ Admin will review the registration request and application may be approved or disapproved. If approved, applicant will receive an email along with login credentials. User may check the email in Junk mailbox if not delivered in the inbox folder. | New account could not be created for a repeat country. Had to use a different country name and different email on 5/2022 | Pass | 1) Country name should be displayed when you hover on flag. 2) Rejected country should get a notification of reject. This did not happen with Timothynwogu10 account. | 1. Country name display is now done 2. We will include the rejection email. One country may have maximum of two admin counts (GMP & GDP). And same email ca;t be repeated to create a new account even of Inspector as well. Done, please verify. | Functionality Clarified
|  | 5 | Terms of Use | Terms of Use | User should be on the landing page | To see the Terms of Use of the RBI Tool | User will click on the Terms of Use link on the bottom of the landing page | Terms of use should be displayed to user |  | Pass
|  | 6 | Privacy Policy | Privacy Policy | User should be on the landing page | To see the Privacy Policy of the RBI Tool | User will click on the Privacy Policy link on the bottom of the landing page | Privacy Policy should be displayed to user |  | Pass
|  | 7 | Contact Us | Contact Us | User should be on the landing page | User can contact PQM+ Admin for any clarification | User will click on Contact Us link on the bottom of the landing page | Contact Us form will be displayed and user will fill the form as needed and will click on Submit. Button. The email will be sent to PQM+ Admin who will respond back to the person sending the request. |  | Pass | We also need a contact us access once logged in… 2) Contact us request did not display in SA access in the tool. 3) NEW COMMENT: developer needs to improve the template to prevent blank screens from being uploaded | There are two types of contact us form. One for the person who is not yet registerd with the RBI Tool. If this person will send a contact us form, it will go via an email and PQM+ Admin will respond it back via email. Secondly, if user is already registered, he /she has rights to use Technical Query which can be accessed from the left-navigation menu. This query also has the attachments feature (up to 5 attachments). This technical form will go to the PQM+ Admin who can see in the RBI Tool, and both sides history of technical queries will be maintained in the Tool. | Functionality Clarified
|  | 8 | Login as Admin | Admin Login | 1. Test Case one is passed 2. Active Country Admin account | Login in to the RBI Tool | On the Landing page, input Email & Password and press Sign In button | If Email and password that were furnished to login are correct, user will be redirected to the dashboard of the RBI Tool otherwise, user will see an error message about the credentials for which login was not successful. |  | Pass
|  | 9 | Profile /Change Password | Profile /Change Password | Logged-in as GDP Country Admin | User can set the display name and can change the password | User will click on the right-top picture image and system will display the profile page where user can set User name that will be displayed after login and user can also change the profile picture and password by providing old password, new password and confirm new password and finnally by submitting the form. | After providing relevant information and after submission of the form, all relevant data should be changed as desired. |  | Pass
|  | 10 | Dashboard Total Counts | Status wise count | Logged-in as GDP Country Admin | To validate total numbers as per the inspection statuses | Verify the total os each status as per the inspection data | If some inspections are in Draft Status, same count should be displayed on the dashboard and same for other status, like Scheduled, In Process, Assessement Completed, Inspection Conpleted, Under CAPA, etc. User can click on each tile and system should take the user to the respective lookup page. | List shows 0 for all types. | Pass |  | This is because you have not yet scheduled any inspection. Please check the counts on the Dashboard. | Functionality Clarified
|  | 11 | View GDP Systems | GDP Systems | Successfully logged in as GDP Country Admin | User can see the already defined GDP Systems that are pre-defined by the PQM+ Admin. These systems are read-only where country admin can only view the systems but can't modify these systems. | From the Left-Navigation menu, user will click on the Configuration menu and will select System from the sub-menu | All GDP Systems should be displayed to the user. | 4 systems displayed | Pass |  | GDP has total 4 systems. Their Sub-System will be displayed along-with their respective Elements assocoated risk rating. | Functionality Clarified
|  | 12 | View GDP Systems Elements | GDP Systems Elements | Successfully logged in as GDP Country Admin | User can see the already defined GDP Systems, Sub System and their respective Elements that are pre-defined by the PQM+ Admin. These systems elements are read-only where country admin can only view the systems elements but can't modify these systems elements. | From the Left-Navigation menu, user will click on the Configuration menu and will select Element from the sub-menu | All GDP System & Sub System wise Elements should be displayed along with pre-defined Risk Rating of each element to the user. | 188 elements displayed with Risk Ratings | Pass
|  | 13 | Search /filter in the data table | Search /filter in the data table | User is already on the Elements table | Searching of any keyword and filtering with the multiple columns of the data table /lookup to narrow-down the desired results. Please note that this functionality available throughout the system in all the modules across the RBI Tool. | Below the column Names (in the white space) user will click and will input the desired keyword to filter the lookup results. User can use this filter for all available columns in the lookup table. Beside this, user can also search in the search field on right-top of the table to seach single keyword across all columns of the lookup table. | After filteration /search, desired results should be displayed to the user. |  | Pass
|  | 14 | Pre-Inspection Tasks | Facilities of an NMRA | Logged-in as GDP Country Admin | Add /Edit /View /Upload Facilities data | From the Left-Navigation menu, click on Pre-Inspection menu and from the sub-menu, click on Facility link. | This will open the Facilities Lookup page of the respective country. |  | Pass
|  | 15 | Facility | Add Facility | 1. Logged-in as GDP Country Admin 2. Currently on the Facility Lookup page | Functionality to add new facility using the form | Click on the + New Facility Fill the form, specially the mandatory fields Press the Submit button | This action should create a new facility and same should be available on the facility lookup page. |  | Pass
|  | 16 | Facility | Edit /View Facility | 1. Logged-in as GDP Country Admin 2. Facility must exist in the lookup | Functionality to modify /View the facility | Identify the facility to edit /view. in the last column of the lookup, under Action column, if you want to view the facility details, click on the Eye icon (Means Read-Only view) otherwise, click on the Pen icon to edit the record to modify. After modifications, click on the Submit button. | This action should save the modified contents of the facility as desired. |  | Pass | Delete option not working . Shold be looked into.
|  | 17 | Facility | u/pload Facility Data | 1. Logged-in as GDP Country Admin 2. Currently on the Facility Lookup page | To upload bulk facilities data using the template | 1. Click on the Download Template button 2. Read instructions inside the template 3. Add data in the template as needed 4. Save template manufacturer sheet as CSV as mentioned in the instructions 5. Press Upload Data button 6. Attach the csv file 7. Press the Submit button | If CSV file is created as per instructions available in side the template, all bulk data of the. Facilities should be available in the facilities lookup page. | Look up table data did not match CSV file uploaded Time is 9 hours ahead. Shouldn’t this use the user time zone? | Under Testing | 5/20 - New comments below by Tim 1) For GDP module, the Delete option in the tool should say :Delete Facility: not manufacturer. 2) The delete option is not workig - could not delete upload done on Apr 29 (ERROR 404 Page not found) 3) Additional empty pages are still carried over with the new upload as of 5/20/2022 4) The facility look up table should have the option to display all records entered in the excel CSV file. For now this is limited to only 6 columns. | Actually facilities are added successfully in the RBI Tool. If you go to the RBI Tool and navigate to Facilities and go to the second last page or last page of the records, you will see those records are there but there were empty rows that were also added in the facilities. Let me clarify this. In the template, by default, I have put formulae and related macros upto 500 rows to make the template size bit less. Now you added about 21 facilities and system imported all the data of 500 rows. You can see the number of pages (shown as 34) on the facilities lookup. To avoid this, you can copy all the actual facilities (including column header) data and paste it in a new sheet to make it a CSV that will contain the records that are required. BTW, this is also being practiced in the MedRS Tool. This was verified during our last meeting that facilities were uploaded accordingly. Please change the status. | Functionality Clarified
|  | 18 | Panel Pool | Panel Pool | 1. Logged-in as GDP country Admin 2.Active email of the Inspector | To create Panel pool members for the GDP inspections. This panel pool will be used to engage the inspector, observers, etc for various inspections across the country | From the Left-Navigation menu, click on Pre-Inspection menu and from the sub-menu, click on Panel Pool link. 1.Click on + New Panel Member button 2. Input all required fields 3. Press the Submit button. Please note that the email you will input against the type of member (Inspector) must be active email and same email should not be blocked. System will create a user of the Inspector role and credentials to login will be sent to the inspector's email. | This action should create a new Panel Member and if new panel member is a Inspector, a user will also be created and credentials to login in the GDP module will be sent to the inspector's email. | Error message: A Database Error Occurred Error Number: 1062 Duplicate entry 'amajoob2@yahoo.fr' for key 'email' INSERT INTO `tbls_user` (`email`, `password`, `userName`, `roleId`, `category`, `countryId`, `profilepic`, `phone`, `status`, `wallpaper`, `createdby`, `createddate`) VALUES ('amajoob2@yahoo.fr', '$2y$10$oi0iMlDaQQ0gfmqpaEx/teITK93x5jHjeww6exgklIPUZKMfMygkm', 'nanavi', 708, 'GDP', '23', 'avatar5.png', '', 'Active', 'wp1.jpg', '205', '29-Apr-22 01:38') Filename: models/LoginModel.php Line Number: 156 | Fail | Panel member was still added suprisingly despite error message | Actually, this user (amajoob2@yahoo.fr) was already created as GDP Admin and was also approved by PQM+ Admin. Here you are trying to create Panel member (Inspector) for the NMRA with same email which is not allowed because of the same emails for 2 different roles. Hope this is now clarified. Did you test it again after my discussion with you during our last meeting | Functionality Clarified
|  | 19 | Inspection Scheduling | Scheduling | 1. Logged-in as GDP country Admin 2. Panel Members are defined | This test case is used to verify the GDP inspection scheduling | From the Left-Navigation menu, click on Scheduling menu and from the sub-menu, click on GDP link. 1.Click on + New Inspection button 2. Input all required fields to baseline facilities aganist facility types for future inspections 3. Press the Assign Panel Members button. 4. System is now ready to add the panel members. 5. Click on Member list and system will show you Member name from Panel Pool you just created before. In the list, you will also see Member Name, Type of Member (Inspector, Observer, etc.) along with Years of experience and Speciality. 6. Select the role of the panel member.Please note that first member will always be the Lead inspector of the inspection. Once selected the Lead inspector, Admin will click on the + sign to add other panel members for the inspection as needed and Admin will select their respective roles for the inspection. 7. To view the selected panel member engagement in the other inspections, click on the Calendar icon. A new tab with the respective panel member inspection calendar will be opened and Admin can see the available slot for the inspection as needed. 8. Select Scheduled from the status list and press the Submit button. Please note that Inspector with LEAD role will be able to access the RBI GDP Tool for the specific inspection. | Admin can view the Inspector's Calendar on a new tab to see his /her engagement for other inspections. Inspection will be scheduled for the facility and LEAD will be assigned to that scheduled inspection. Lead Inspector can also see the scheduled inspection on his /her dashboard and lookup table under Inspection Menu. You can see the status of each inspection that could be in different phases of the inspection lifecycle. First Stage = Scheduled Second Stage = In Process Third Stage = Inspection Completed Fourth Stage = Under CAPA Fifth Stage = Inspection Approved Fifth-A Stage = Inspection Deferred and Closed |  | Under Testing | Tim 5/20/22: 1) We will need to add "Baseline Inspection" to list of inspection options under new inspections tab. The facilities will first get a baseline before being scheduled for routine. Otherwise, scheduling works fine. | Stages are now as per our discussion with Tefari on the GMP Module and same is incorporated in GDP. Please check.
|  | 20 | Inspection Execution | Execution | 1. Inspection is Scheduled | Admin can see the processing of various phases of the inspection | From the Left-Navigation menu, click on Inspection and then from the Sub-Menu, select GDP. Admin can see inspections lookup table from where Admin can view the details of the inspection execution by Editing the specific inspection under Action column. | Inspection Lookup page and then after editing the specific inspection, all tabs of the inspection will be available to be reviewed. |  | Pass
|  | 21 | Reference Library | Reference Library | 1.Logged-in as GDP Admin | To create Reference Library for the NMRA Admin and Inspectors | User will click on the Reference Library from the Left-Navigation menu. | Reference Library lookup table will be displayed to user |  | Pass
|  | 22 | Reference Library | Add Reference Library | 1.Logged-in as GDP Admin | This test case will be used to add Reference Library | 1. User will click on + New Reference Library 2. User will input all required details 3. User will attach Electronic version 4. User will click on Submit button | New Reference Library will be created and will be available to users. | Alert says "New record saved successfully" but no document was added to the table. Attempted to add a pdf doc 137kb | Pass |  | Are you able to see the reference library contents? Also Reference Library document link is now attached to the main lookup view as discussed. | Bug Fixed
|  | 23 | Inspection Status | Inspection Status | 1.Logged-in as GDP Admin | Admin is authorized to set status of any inspection to any stage. If inspector has changed the inspection status and same status can't be reverted back by the inspector, here Admin can change the inspection status on behalf of inspector | 1. Edit the inspection 2. at the bottom of the inspection, set appropriate status as desired 3. Press Submit button | Inspection should be now in the desired status. |  | Pass
|  | 24 | Reports | Reports | 1.Logged-in as GDP Admin 2. Multiple Inspections are already conducted | To see pre-defined reports in the GDP modules | To be developed after functional testing and based on the inspection data for various manufacturers. |  | Error: A Database Error Occurred Error Number: 1146 Table 'pqmplustools_rbi-test.tbl_manufacturer' doesn't exist SELECT `BaseTbl`.* FROM `tbl_manufacturer` as `BaseTbl` WHERE `BaseTbl`.`isDeleted` = 0 AND `BaseTbl`.`status` = 'Active' Filename: models/MyModel.php Line Number: 1016 |  |  | Please check this test case and set the appropriate status.
|  | 25 | Switching between GMP & GDP | App Switching | 1. You are uou the RBI Tool Landing Page 2. GMP and GDP logins are created | RBI Tool is a single interface for both GMP and GDP modules. Before switching to any module (GMP or GDP), you must have active logins for both. | To switch to GMP module, input GMP login credentials To switch to GDP module, Logout from GMP Module and input GDP login credentials | Using the same RBI Tool landing page: Upon login to GMP module, user will only see the GMP module Upon login to GDP module, user will only see the GDP module | Not tested. - No GMP credentials available |  |  | Please check this test case and set the appropriate status.
|  | 26 | IRIMS Compatibility | Integration with IRIMS | 1. There should be an IRIMS software 2. IRIMS should be capable to be integrated 3. Need to identify integration points 4. Need to develop Application Programming Interface (API) RESTful API from both ends, where applicable 5. Testing of integration process | This test case /deliverable can't be tested untill ot unless the pre-requisites are not fully met. | Based on the integration, RBI inspection should be triggered from the IRIMS (When RBI will be integrated with IRIMS) and same will be shown in the RBI Tool and once inspection is completed, from RBI Tool, same inspection will be sent to IRIMS by using the Application Programming Interfaces (APIs) | From IRIMS, Inspection should be shown in the RBI Tool From RBI Tool, executed inspection details should be visible in IRIMS |  |  |  | Please check this test case and set the appropriate status.
|  | 27 | Google Map Links | Google Map | 1. Need to have Google Map API 2. Need to identify the Google Map requirements where to display 3. Need to identify the map criteria | Map of cities and regions can be seen in the software by purchasing the Google Map APIs from Google. These APIs will be used in RBI Tool to show the respective maps. We need to decide where to show the map and what will be the criteria to show the map. | This test case needs to fulfil the pre-requisite to move forward | Once pre-requisite is met, user could see the respective map on the designated secvtion of the Tool. |  |  |  | Please check this test case and set the appropriate status.
|  | 28 | Instructional Guide | User Operational Manual | Once all test cases are executed /passed | User can see the operational manual that will facilitate user to see functionality of various modules with the help of graphical user interfaces (GUIs) and their respective description. | Read the Operational Guide as per user role and module /sub module, as appropriate and as needed. | Desired functionality should be available in the Operational manual of the RBI Tool. |  |  |  | Please check this test case and set the appropriate status.
|  | 29 | Technical Query | Technical Support from PQM+ | User is logged into the RBI Tool | This test case is used to check the functionality of the newly added feature of technical queries for the registered user from NMRA.User should be able to create new technical query request and same request should go to the PQM+ Admin who should respond back to the sender. | 1. Click on the Technical Query link from the left-navigation menu 2. New lookup interface will be opened. 3. Click on New Query button from top-right of the lookup 4. New Query form will be opened 5. Fill-in the required fields indicated with mandatory fields indicator (*) 6. Optionally, attach upto 5 files in pdf format and less than 5mb in size 7. Click on Submit button to send the technical query to PQM+ Admin 8. A new record in the Lookup table should be shown. 9. When PQM+ Admin will respond back, user should also see isame in the sam lookup table. | User should be able to send a new technical query to PQM+ Admin and can also see the queries in the lookup table along-with the reply from the PQM+ Admin when he /she replies | Super Admin not able to see excel doc attached. Make file extensions open | Under Testing |  | Please check this test case and set the appropriate status.

## GDP Inspector
Tester Name | Test Date | Test Case No. | Function Name | Subm Function | Pre-requisite | Test Description | Test Step Details /Data input | Expected Results | Actual Results | Tester Status | Suggestions | Developer's Response | Developer's Status
Thomas Benin - NMRA inspector | 2022-05-20 | 1 | Access RBI Tool URL | RBI Tool Test URL | 1. Internet Connection 2. Access the Google Chrome browser | To open the RBI Tool Landing page | Input this URL and press Enter key https://www.rbi-test.pqmplustools.com | Landing page of the RBI Tool |  | Pass |  | Please test and set status against this test case.
kilo-ouatt@hotmail.com |  | 2 | I forgot my password | Forgot Password | 1. Test Case one is passed 2. Active Country Inspector account | To reset your forgotten password | Below the Sign In button, click on I forgot my password link | System should take you to the RBI Tool password retrievel page | I did not get the new pw credentials in my email or junk email | Under Testing |  | Please test and set status against this test case.
|  | 3 | I forgot my password | Forgot Password | 1. On the RBI password retrievel page 2. You email should be active email 3. Email should not be blocked | To reset your forgotten password | Input your Inspector Email and Verification Code and Press the Request New Password button | You should receive an email for the confirmation of password reset. When you will confirm the email then you will get another email with new auto-generated password from the RBI Tool that you can use to login. |  | Under Testing |  | Please test and set status against this test case.
|  | 4 | Terms of Use | Terms of Use | User should be on the landing page | To see the Terms of Use of the RBI Tool | User will click on the Terms of Use link on the bottom of the landing page | Terms of use should be displayed to user | Displayed | Pass
|  | 5 | Privacy Policy | Privacy Policy | User should be on the landing page | To see the Privacy Policy of the RBI Tool | User will click on the Privacy Policy link on the bottom of the landing page | Privacy Policy should be displayed to user |  | pass
|  | 6 | Contact Us | Contact Us | User should be on the landing page | User can contact PQM+ Admin for any clarification | User will click on Contact Us link on the bottom of the landing page | Contact Us form will be displayed and user will fill the form as needed and will click on Submit. Button. The email will be sent to PQM+ Admin who will respond back to the person sending the request. | Indicated email sent successfully but No email received by admin | Fail |  | Dr. Souly is the Admin of PQM+. Plz check with him to see the email. He might have received email in his junk / spam folder. | Functionality Clarified
|  | 7 | Login as Inspector | Inspector Login | 1. Test Case one is passed 2. Active Country Inspector account | Login in to the RBI Tool | On the Landing page, input Email & Password and press Sign In button | If Email and password that were furnished to login are correct, user will be redirected to the dashboard of the RBI Tool otherwise, user will see an error message about the credentials for which login was not successful. | log in successful for account (Thomas Inspector) | Pass
|  | 8 | Profile /Change Password | Profile /Change Password | Logged-in as GDP Country Inspector | User can set the display name and can change the password | User will click on the right-top picture image and system will display the profile page where user can set User name that will be displayed after login and user can also change the profile picture and password by providing old password, new password and confirm new password and finnally by submitting the form. | After providing relevant information and after submission of the form, all relevant data should be changed as desired. |  | Pass
|  | 9 | Dashboard Total Counts | Status wise count | Logged-in as GDP Country Inspector | To validate total numbers as per the inspection statuses | Verify the total os each status as per the inspection data | If some inspections are in Draft Status, same count should be displayed on the dashboard and same for other status, like Scheduled, In Process, Assessement Completed, Inspection Conpleted, Under CAPA, etc. User can click on each tile and system should take the user to the respective lookup page. | A scheduled inspection was not counted in the dashboard tile | Pass |  |  | Bug Fixed
|  | 10 | Inspection Execution | Execution | 1. Logged-in as GDP Country Inspector 2. Admin has assigned some inspection to you as a LEAD Inspector | Inspector will start execution of the inspection using various steps. | From Left-Navigation Menu, click on Inspection menu and then select GDP from the sub-menu | This should display GDP Inspection lookup table to the GDP Inspector |  | Pass
|  | 11 | Inspection Execution | Edit GDP Inspection | 1. Inspector should be on GDP Inspection lookup page 2. Inspection execution date is still valid 3. Inspection Status should be "Scheduled" | Edit GDP Inspection | 1. Identify the Inspection to edit 2. Click on Pen icon frpm the Action column | After confirmation from the user, Inspection will be opened in Edit mode |  | Pass
|  | 12 | Inspection Execution | Scheduling Tab | Specific Inspection is opened to edit | To view the GDP Inspection schedule detail. Information on this tab is read-only for the Inspector. | Inspector will scroll up and down to view the inspection schedule detail | Scheduling tab should be available to GDP Inspector in Read-only mode to view the schedule. |  | pass
|  | 13 | Inspection Execution | Inspection Tab | Specific Inspection is opened to edit | On this tab, Inspector will download the Inspection Agenda that will be generated by the RBI Tool itself along-with pre-entered relevant into it. Inspector can also upload Site Master File and QIS File. Beside uploads, Inspector can also input Opening Meeting comments in the Inspection Tab. Few other updates would be required on the same tab, like Closing Meeting Remarks, Uploading Inspection Report. This will be done once Inspection is completed | 1. Click on Agenda Template button to download relevant agenda for this inspection 2. Prepare the Agenda and upload it back in the inspection. 3. Upload Site Master File 4. Upload QIS File 5. Input Opening Meeting Remarks | As per given steps, all functionality should be performed without any issue | 1Agenda template says PQM+. With | Under Testing | 8/16/22 (Template info need to be further refined for GDSP Inspections) #1). Agenda should be country Specific (for Example it should indicate the Country of Inspector - Benin.) # 2). Remove PQM from Template title and use country name (in Bold or color) instead. #3) the agenda should be able to pull from the tool the systems to be inspected (based on inspector selections in the tool) into (page 2). #3)The report template should also pull information based on what is already completed in the tool. | 1. GDP Agenda is now updated.Plz check. 2. Plz check the submission again. 3. Uploading the Agenda file is fixed. Plz check and verify. | Bug Fixed
|  | 14 | Inspection Execution | Assessment Tab | 1. GDP Systems are defined 2. System Wise Elements are defined 3. Element Wise Risk Rating is defined | On this tab, Inspector will assess all the relevant elements of each system by giving GDP Rating against each relevant element which will multply the Risk Rating with GDP Rating and Overall Score will be calculated. GDP Ratings: 1. Not Compliant 2. Partially Compliant 3. Compliant | 1. Using Filter options, select the desired System and /or Sub-System 2. For further filteration on Elements, search the required element, if required 3. Select GDP Rating from 1 to 3 as described in Test description column (Not Assessed and Not applicable were added) 4. In the Observation column, input the rationale of given GDP Rating. 5. Do the same against all elements of various systems 6. To verify all the data is saved and to change the inspection status from Scheduled to In Process, select Proceed from the Status list and click on Submit button. If Inspection iis scheduled for multiple days, then after saving the inspection, reopen the inspection on the next day for remaining Assessment part of the inspection and do the same steps for the remianing elements.. | 1. Against a System Element, GDP Score is selected 2. Overall Score will be automatically calculated 3. Observations are stored 4. After saving the record, re-open the same inspection and verify all the data that was input in previous steps. | Could not proceed beacause no data was entered in mandatory observation - Should this"Observation Field" be mandatory???? Need to confirm with Gabriel… 6/27/22 | Pass | Tim 5/20/22: 1) What happens when a GDP element is not applicable to a facility based on its class. Can there be an option for NA, which also eliminates this element from the final GDP Overall Score? 8/16/22. 1) Please make the info in the "Column visibility" available. Element risk rating is not available and it should be. | This test case is meant for the assessment tab only. Means Selecting a System /Sub System and selecting the appropriate score against respective element and description against the given score. Now if Overall Score is being calculated correctly then this use case should be passed, else this will be considered as fail. The error message is now removed. Please check and verify. | Bug Fixed
|  | 15 | Inspection Execution | Assessment Report Tab | 1. Assessment of the Elements is completed 2. Your Current Tab is Assessment Report | Once System Wise elements GDP Rating is completed, Tool will automaticaly generate Assessment Report. This report will calculate the following: 1. Element Count 2. Element Assessed 3. Grand GDP Point 4. Possible GDP Point 5. Grand OSC Point 6. Total Risk Rating 7. Possible OSC Point 8. GDP Score 9. Grand OSC | 1. Click on Assessment Report tab and then verify the calculations. 2. Below this table, you cn also see the totals of all the systems | Calculation should be as desired and as per given formulae | Need to Discuss calculations and Formula with Teferi Is accronym OSC correct or should it be OCS New Calculation in the tool is not working accordingly. Facility and Documentation were entered as 2 and 1 across all elements and this is not reflected in the calculated scores. Please check the formolua in the tool to ensure it is working accordlingly. 6/27/22 | Under Testing | The calculation is not working correctly here…it is reporting partially compliant for a facility with a perfect score. 8/16/22 1. Please revise calculator descritption pop-up 2. The facility inspection report should contain the summary of the inspection findings, filled from the tool, with the observations and cateegorization reported accordingly | Please discuss the calculations with Tefari and let's conclude this test case accordingly.
|  | 16 | Inspection Execution | Compliance Tab | 1. Assessment Report is Verified 2. Your Current tab is Compliance | Now user will see the System-wise and Company-wise Compliance Level on this tab which will be automatically calculated as below: 1. Not Compliant 2. Partially Compliant 3. Compliant | 1. Click on the Compliance Tab 2. View System Wise Compliance Level 3. View Company Compliance Level | Verify System and company Compliace Levels as desired | At 100 GDP Score System 1 (QMS) is still reported as partial compliance for system with 100% compliance. | Pass | Scoring appears to be accurate. | Compliance is calculated based on Grand OSC score. For QMS, Grand OSC score is 78 and this 78 score falls under Partially compliance category. (From 51 to 80) | Functionality Clarified
|  | 17 | Inspection Execution | System Dashboard Tab | 1. Assessment Report is Verified 2. Your Current tab is System Dashboard | This Test case is used to see the Element Count and Possible Score values | 1. Click on System Dashboard tab 2. View System wise Element Count and Possible Score values | Verify the calculations | When changed reduced or corrected, the Dashboard element count did not reflect the updated count | Pass |  | When you change any GDP score value, it's reflected in the Overall score and other calculations as well. Let's discuss it ASAP. | Functionality Clarified
|  | 18 | Inspection Execution | Assessment Completed | 1. System-wise Elements are assessed 2. Assessment Report is verified 3. Compliance Level is verified 4. System Dashboard is verified | Now it's time to move the Inspection from In Process to Assessment Completed phase | !. Select Proceed from the Status dropdown 2. You will see a message stating as "Inspection saved with "Assessment Completed" status can not be edited, Are you Sure?". This means that all your assessment is up to mark and you are finalizing the Assessment. If you Submitthe inspection, Inspection will be saved under Assessment Completed status which means no elements GDP rating is editable, however Inspector can write Closing Meeting Remarks, can upload the Inspection Report and can give an overall Rating to the Company.. | 1. Now System should show the Inspection status as Assessment Completed. 2. Inspector can't modify any element scoring /rating. 3. If by-mistake status was changed, GDP Admin has right to modify the inspection status as needed. | A Database Error Occurred Error Number: 1054 Unknown column 'grandGdpPoint' in 'field list' UPDATE `tbl_gdpinspectionassessmentdetail` SET `isDeleted` = '0', `elementCount` = '57', `elementAssessed` = '57', `grandGdpPoint` = '171', `possibleGdpPoint` = '171', `grandOscPoint` = '399', `totalRiskRating` = '133', `possibleOscPoint` = '513', `gdpScore` = '100', `grandOsc` = '78', `updatedby` = '208', `updateddate` = '09-May-22 20:49' WHERE `id` = '13' Filename: models/LoginModel.php Line Number: 168 | Pass | Add Facility level descriotion and compliance criteria under Compliance tab | The error message is now removed. Please check and verify. | Bug Fixed
|  | 19 | Inspection Execution | Upload Inspection Report | Assessment is completed | To upload Inspection report that was based on system-generated template and finalized by the inspector. | 1. Click on Inspection tab 2. Click on Inspection Report Template 3. Finalize the report 4. Upload Inspection Report 5. Select Proceed from the status list to move the inspection from Assessment Completed to Under CAPA. | 1. When you download Inspection Report Template, it should have the basic information of the inspection and in the last section, Assessment Report table will also be available. 2. You should see the Inspection Status as Under CAPA 3. On the Inspections' tab, you will see an ew tab with the caption of CAPA |  | Pass | 1.The inspection report template should be available after completion of activities in the assessment report Tab. 2. The facility inspection report should contain the summary of the inspection findings, filled from the tool, with the observations and cateegorization reported accordingly 3. I do not see a tab for CAPA (Showed up after log out and back in) | Please test this test case and set the appropriate status.
|  | 20 | Inspection Execution | Under CAPA | Inspection Status is now showing Under CAPA | Now all tabs are disabled except CAPA tab where now inspector will download the CAPA template and after finalizing the CAPA document, inspector will upload the CAPA. | 1. Click on CAPA tab 2. Click on CAPA Template button 3. CAPA template will be downloaded 4. Finalize the CAPA document 5. Upload CAPA document 6. Send CAPA email to company | CAPA followup needs to be recorded and verified. Is CAPA document is to be sent to the company via email? |  |  | Capa template was pre-populated accordingly | Please test this test case and set the appropriate status.
|  | 21 | Inspection Execution | Inpsection Completed | Inspection current status should be Under CAPA. | This test case is to set the Inspection status as Inspection Completed. | Inspector has an option to send CAPA tp the company that was finalized. To do so, Select Yes from the list indicating Send CAPA Email to Company under CAPA tab. Once CAPA follow-up is completed, mow it's time to complete the Inspection. Select status of the inspection as Proceed and then click on Submit button. | Inspection Status will be changed from Under CAPA to Inspection Completed This will make complete inspection as read-only for the inspection. Now based on the Inspector report and compliance level and CAPA output, GDP Admin will finally Approve or Inspection Approved or Inspection Deferred and Closed as the case may be. |  |  | A completed inspection for Benin - Thomas inspector was completed but iy did not show up under the NMRA admin list of completed inspections. Need to include Compliance criteria under Compliance tab | Please test this test case and set the appropriate status.
|  | 22 | Reports | Reports | 1.Logged-in as GDP Inspector 2. Multiple Inspections are already conducted | To see pre-defined reports in the GDP modules | To be developed after functional testing and based on the inspection data for various manufacturers. | System Dashboard |  |  | Dashboard pie charts can be improved. What information are we trying to convey? Please make pop-ups more readable - increase font size | Please test this test case and set the appropriate status.
|  | 23 | Reference Library | Reference Library | 1.Logged-in as GDP Inspector | To View Reference Library that was created by the Admin | User will click on the Reference Library from the Left-Navigation menu. | Reference Library lookup table will be displayed to user |  |  | Why do we need the additional page 2? Can we add the recorods from page 2 into table on page 1? | Please test this test case and set the appropriate status.
|  | 24 | Reference Library | View Reference Library | You are on Reference Library page | This test case will be used to view already defined Reference Library | 1. User can search the desired document from the search and filters 2. User can select Document Link from the Action column (Last Column using the dropdownlist | Desired Reference Library document should be opened |  |  |  | Please test this test case and set the appropriate status.
|  | 25 | Switching between GMP & GDP | App Switching | 1. You are uou the RBI Tool Landing Page 2. GMP and GDP logins are created | RBI Tool is a single interface for both GMP and GDP modules. Before switching to any module (GMP or GDP), you must have active logins for both. | To switch to GMP module, input GMP login credentials To switch to GDP module, Logout from GMP Module and input GDP login credentials | Using the same RBI Tool landing page: Upon login to GMP module, user will only see the GMP module Upon login to GDP module, user will only see the GDP module |  |  |  | Please test this test case and set the appropriate status.
|  | 26 | Instructional Guide | User Operational Manual | Once all test cases are executed /passed | User can see the operational manual that will facilitate user to see functionality of various modules with the help of graphical user interfaces (GUIs) and their respective description. | Read the Operational Guide as per user role and module /sub module, as appropriate and as needed. | Desired functionality should be available in the Operational manual of the RBI Tool. |  |  |  | Please test this test case and set the appropriate status.
|  | 27 | Technical Query | Technical Support from PQM+ | User is logged into the RBI Tool | This test case is used to check the functionality of the newly added feature of technical queries for the registered user from NMRA.User should be able to create new technical query request and same request should go to the PQM+ Admin who should respond back to the sender. | 1. Click on the Technical Query link from the left-navigation menu 2. New lookup interface will be opened. 3. Click on New Query button from top-right of the lookup 4. New Query form will be opened 5. Fill-in the required fields indicated with mandatory fields indicator (*) 6. Optionally, attach upto 5 files in pdf format and less than 5mb in size 7. Click on Submit button to send the technical query to PQM+ Admin 8. A new record in the Lookup table should be shown. 9. When PQM+ Admin will respond back, user should also see isame in the sam lookup table. | User should be able to send a new technical query to PQM+ Admin and can also see the queries in the lookup table along-with the reply from the PQM+ Admin when he /she replies |  |  |  | Please test this test case and set the appropriate status.

## GDP Inspector - Mobile App
Tester Name | Test Date | Test Case No. | Function Name | Subm Function | Pre-requisite | Test Description | Test Step Details /Data input | Expected Results | Actual Results | Tester Status | Suggestions | Developer's Response | Developer's Status
|  | 1 | App Installation | Android based App Installation | 1. Mobile App (APK File) should be available to be installed 2. Android based device (Smart Phone or Tablet) having > = 5 (Lolipop) | Installation of of RBI Tool that will contain Offline versions of GDP module for Inspectors | 1. Tap on the APK file 2. Tap on Open 3. Tap on Install | You will see a new icon with the name of Risk Based Inspection with RBI Tool Logo
|  | 2 | Open RBI Mobile App | RBI Mobile App | RBI Mobile App is installed on your device | Open the App and login in to the App | 1. Tap on the Risk Based Inspection icon 2. You will see the Flash Screen with PQM+ Logo and App Name GMP & GDP 3. After Splash Screen, you will see short description of each module. 4. On the same page, you can also see the Terms of Use and Privacy Policy links 5.Slide the page from right to left 6. You will be on Login page 7. Input your registered email & password 8. Click on Login button | 1. You can see the Splash Screen 2. You can readt Terms of Use 3. You can read Privacy Policy 4. You can login into the App by providing valid email and password 5. After login you will be om the listing page of assigned inspections by your admin
|  | 3 | Inspection Main page | Inspections Listing Page | 1. You are logged-in as an Inspector 2. Some inspection is assigned to you | Inspection details can be seen on this interface, whewre each inspection will be on one card and each card will show the Inspection Start Date, Inspection End Date, Company Name, Inspection Type, Form of Inspection and Status of the inspection | On the top-right side, tap on Refresh icon that should fetch new inspections assigned to you, if any. | Inspector can see all assigned inspections and inspection on which he /she is already working on.
|  | 4 | Inspection Execution | Inspection Execution | At least one inspection is assigned to the inspector | Inspector will start execution of the inspection | 1. On top-right of the respective inspection card, tap on three horizontal dots (…) 2. From the dropdown menu, tap on Edit 3. App will load all components of the inspection, like a. Load Data b. Scheduling c. Inspection d. Assessment e. Assessment Report f. Compliance g. System Dashboard 4. App will also show the Geo Location icon. So when Inspector will be onsite, Inspector can use this icon to get location of the site and same will be saved in the database for future reference. | Inspector should see these links after Inspector will tap on Edit link from the menu: a. Load Data b. Scheduling c. Inspection d. Assessment e. Assessment Report f. Compliance g. System Dashboard h. Geo Location
|  | 5 | Inspection Execution | Load Data from server | 1. Inspector is on Inspection page 2. Your have an active Internet connection | Inspector will load data from the server for the inspection. | 1. Tap on Load Data from server button 2. You will see a message at the bottom about the data upload status Use this feature when you are connected to the internet | 1. You should see the data load success message. 2. Load Data from server button should be disappeared after data is loaded.
|  | 6 | Inspection Execution | View Inspection Schedule | Inspectior is on Inspections page | Inspector can view the Inspection schedule | 1. Tap on the Scheduling icon 2. View the scheduling data | Scheduling page should be displayed with the details of the inspection schedule.
|  | 7 | Inspection Execution | Inspection Page | Inspectior is on Inspections page | Inspector can view and edit the Inspection data | 1. Tap on the Inspection icon 2. If you open this Inspection icon first time, you will have to Allow the RBI Tool to access the Media and photos from the device. 3. Inspector has an option to upload Inspection Agenda, Site Master File and QIS File from the App. 4. Inspector will set the Status to In Process to let system know that Inspector has started the Inspection execution process. | Inspector can upload the files and can see the uploaded files accordingly.
|  | 8 | Inspection Execution | Assessment Page | You have already loaded data from the server | On this test case, Inspector will test the following: 1. System /Sub Sustem 2. System Elements 3. GDP Rating 4. Risk Rating 5. Overall Score 6. Observation | 1. Tap on Assessment icon 2. App will display a message to Select the system first 3. Tap on System list 4. You see the 4 systems of GDP 5. Select on the system that you want to start with and then you will have another option to further narrow-down the Elements listing by selecting the Sub-System. This will further filter the elements 6. You will have the option to search for an Element or you can start assessing the elements in sequence or by scrolling. 7. Tap on the Element 8. in the new window, you can see the Element Name, GDP Rating, Risk Rating (already defined) and Observation. 9. You just need to select the appropriate GDP Rating and Observation. 10. To save tap pn Update link Inspector will repeat this exercise for all other relevant system and their respective elements. Inspector must give observations against the assessed score /rating as this will prepare the CAPA document. | For this particular element that was assessed by the inspector, App will go back to the previous list of elements and inspector can see the Overall Score along with the selected value of GDP Rating.
|  | 9 | Inspection Execution | Assessment Report Page | GDP System and their respective elements' assessment is completed. | Inspector will verify the Inspection report based on the assessment. | 1. Inspector will tap on the Inspection Report 2.System wise (one-page) all calculations will be shown 3. For next page, slide the page from right-to-left 4. Orange color cell intimates the Inspector about any. Missing element that might have overlooked for the assessment process. | Inspector needs to verify /vet the Assessment report as below: 1. Element Count 2. Element Assessed 3. Grand GDP Point 4. Possible GDP Point 5. Grand OSC Point 6. Total Risk Rating 7. Possible OSC Point 8. GDP Score 9. Grand OSC
|  | 10 | Inspection Execution | Compliance Page | 1. GDP System and their respective elements' assessment is completed. 2. GDP Inspection Report is verified | Now's it's time to see the system Level and Company Level Compliance as shown below: 1. Not Compliant 2. Partially Compiant 3. Compliant | 1. Tap on the Compliance icon 2. Next page wiill be splitted into 2 portions, Top one will show System wise GDP Score, Overall Score and System Level Compliance. Whereas bottom portion will show the Total GDP Score, Total Overall Score, GDP Score Average, Overall Score Average and Overall Company Compliance Level | Inspector to verify System Level and Company Level Compliance
|  | 11 | Inspection Execution | System Dashboard | All System Level Elements are defined | 1. To see System wise Element Count 2. To see Possible Scores 3. To see Grand Element Count 4. To see Possible Element Count | 1. Tap on the System Dashboard icon 2. System wise Element Count and Possible Score will be displayed 3. To verify other systems, slide from Right-to-left. | Inspector will verify the 1. Element Count. 2.` Possible Score 3. Grand Element Count 4. Possible Element Count
|  | 12 | Sync Inspection | Inspection Sync with the server | 1. Inspection Status is Assessment Completed | This test case will sync the off-line inspection record with the live server of the NMRA. | 1. On the main GDP Inspection interface, on the respective inspection card, tap on three horizontal dots (…) means menu of that particular inspection. 2. You will see a new menu option other than Edit and View as Sync. Tap on this option 3. This will synchronize offline inspection data with the live server where user can see same offline data from the web interface | Offline data should now be available on the live server and user can use the web interface of the RBI Tool to see the inspection record that was comleted using Android based Offline assessment
|  | 13 | Delete offline Inspection | Delete offline inspection data | Inspection is already Sync with the server | If Inspector wants to delete the offline inspection data to save the storage on the device, user can delete the inspection data that was already sync with the server. Delete option can only be available once inspection is Sync with the server. | 1. On the main GDP Inspection interface, on the respective inspection card, tap on three horizontal dots (…) means menu of that particular inspection. 2. You will see a new menu option as Delete. Tap on this Delete option 3. This will delete offline inspection data from the offline device. | Local data of the respective inspection is deleted from device.
|  | 14 | Inspector Profile | Profile | Logged in as RBI Inspector | To view /Edit the profile of the Inspector | 1. Tap on top-right of the App; 3 vertical dots (⋮) to open the menu 2. Tap on Profile 3. User can see the following in profile: a. Inspector Picture (Which is Changeable) b. Name of the inspector (Not Changeable) c. Email (Not Changeable) d. NMRA (Not changeable) e. GDP Inspector (Not Changeable) | Inspector can change his /her picture in the RBI Tool.
|  | 15 | Contact Us | Contact Us | Inspector may need some help, so he /she can fill the form and same will go to the Admin of the respective NMRA | To contact NMRA Admin, Inspector can fill the form within App | 1. Tap on top-right of the App; 3 vertical dots (⋮) to open the menu 2. Tap on Contact Us 3. Inspector Name, Email will be pre-filled 4. Inspector will need to describe the issue and will tap on Submit button. 4.1 Inspector may also leave this form by tapping onGo Back button | Contact Us emaill should reach to the Admin
|  | 16 | Logout | Logout | Inspector is already logged-in. |  | 1. Tap on top-right of the App; 3 vertical dots (⋮) to open the menu 2. Tap on Logout User Email and password will be saved in the app. | User should be logged out from the app

## GDP Missing Functionality
Sr. No. | Function Nme | Sub Function Name | Missing Functionality | Remarks